## Eng
No | KCP | KPI | KPI_Definition | KPI_Formula | Conditions | Baseline | SLA
1 | MOS-QCL1 | MOS-QCL1 Period | Average period from MOS to QCL1 approval completion time of the DU within the statistical period. | Average: Sum(MOS-QCL1 Period)/ Total MOS according to condition in the current month | Condition: MOS actual & QCL1 date not empty MOS-QCL1 Period >=0, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Calculation: Average(MOS-QCL1 Duration) | QC - 14 days QC + PAT - 21 days | -
1.1 | MOS-QCL1 | One flow Completion rate | MOS-QCL1 DUs completed within xx days/Total number of DU completed MOS of the month (Remark : Cut off day will be on the 14th of the following month) | (QC L1 approval completion time - MOS actual end time)< = 14 days of DU/ Total number of MOSs in the current month | Condition: MOS date & QCL1 date not empty, MOS-QCL1 Duration between -5 and Baseline (14/21), INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: MOS date. Denominator: Total MOS date | Based on the country | -
2 | MOS-Installation | MOS-Installation Period | Average period from MOS to installation completion of DU within the statistical period. | Average: Sum(MOS-INSTALL Period)/ Total MOS according to condition in the current month | Condition: MOS date & Installation date is not empty MOS-INSTALL Duration >=0, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y' Calculation: Average(MOS-INSTALL Duration) | - | 7days
2.1 | MOS-Installation | Timely admission rate | Number of DUs with site activity attendance within three days after the MOS actual completion date/Number of DUs completed by MOS | Earliest Clock in Date - MOS actual end date <=3Days / Total MOS by the current month | Condition: INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: MOS Actual End Date - Clock In Date <= 3 Days). Denominator: Total MOS Date | 0.8 | 3days
2.2 | MOS-Installation | Job Continuity | Whether the team continues to clock in and out until Installation is completed Formula: Number of days with clock in attendance along with site sign and site verify date in the period of MOS-Installation/Total number of days in MOS-Installation | Days of clock in between MOS-INSTALL / MOS-INSTALL Period | Condition: MOS date & Install Date is not empty, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: Clock In records in between (MOS-INSTALL) Denominator: MOS-INSTALL Duration +1 (ALL_DAYS) | 0.7 | -
2.3 | MOS-Installation | Multi-DN/Multi-MOS | Number of sites with DN delivery > = 2/Total number of sites with MOS completion (excluding DUID) | Count Site SITE_COUNT >=2 / Total Site ID | Condition: INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: Count Site SITE_COUNT >=2 Denominator: Total Site ID | 0.15 | -
3 | Installation - QCL1 | Installation - QCL1 Cycle | Average period from the DU installation to the completion of the first review by the QC within the statistical period. | Average: Sum(INSTALL-QCL1 Period)/ Total INSTALL according to condition in the current month | Condition: INSTALL actual end - QCL1 date is not empty INSTALL-QCL1 Period >=0, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Calculation: Average(INSTALL-QCL1 Duration) | QC - 7 days QC + PAT - 14 days | -
3.1 | Installation - QCL1 | Timely admission rate of QC | Number of QC Save Start Time (QC Save Start Time) performed within three days after the installation is completed/Number of DUs completed | QC Save Begin Date - INSTALL Actual End Time <= 3days / Total DU according with condition | Condition: SAVE_BEGIN_DATE not empty, FIRST_SUBMIT_APPROVE_TIME not empty, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: SAVE_BEGIN_DATE - INSTALL ACTUAL_END_TIME <= 3days. Denominator: Total DU | 0.9 | -
3.2 | Installation - QCL1 | Timely QC collection rate | Time from the start of the QC task (Save Start Time) to the time when the QC task is submitted for the first time/Total number of QCL1 tasks submitted | FIRST_SUBMIT_APPROVE_TIME - SAVE_BEGIN_DATE <=3days / Total DU according with condition | Condition: SAVE_BEGIN_DATE not empty, FIRST_SUBMIT_APPROVE_TIME not empty, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: FIRST_SUBMIT_APPROVE_TIME - SAVE_BEGIN_DATE <= 3days. Denominator: Total DU | 0.8 | -
3.3 | Installation - QCL1 | QCL1 Timely Approval Rate | (L1 approval completion time - QC first submission time) Number of tasks/Total number of manually approved tasks | L1_REVIEW_END_TIME - FIRST_SUBMIT_APPROVE_TIME <= 1 Day / Total DU according with condition | Condition: L1_REVIEW_END_TIME not empty, FIRST_SUBMIT_APPROVE_TIME not empty, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: L1_REVIEW_END_TIME - SAVE_BEGIN_DATE <= 3days. Denominator: Total DU | 0.9 | -
3.4 | Installation - QCL1 | QCL1 First Time Pass Rate(FTPR) | Number of DUs with the first time pass with QCL1 approval | L1_REVIEW_END_TIME - L1_FIRST_REVIEW_END_TIME / Total DU according with condition | Condition: L1_REVIEW_END_TIME not empty, L1_FIRST_REVIEW_END_TIME not empty, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: L1_REVIEW_END_TIME - L1_FIRST_REVIEW_END_TIME <= 15seconds. Denominator: Total DU | 0.9 | -
4 | QCL1-QCL2 | QCL1-QCL2 Period | Average period from the completion of the QCL1 review to the completion of the QCL1 review within the statistical period. | Average: Sum(QCL1-QCL2 Period)/ Total QCL1 according to condition in the current month | Condition: QCL2 date and QCL1 date is not empty MOS-QCL1 Period >=0, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y' Calculation: Average(MOS-QCL1 Duration) | 14 days | -
4.1 | QCL1-QCL2 | QCL2 Timely Review Rate | (L2 first review completion date - L1 approval completion date) Number of tasks/Total number of tasks approved by L1 | count (L2_FIRST_REVIEW_END_TIME - L1_REVIEW_END_TIME) <=7 day DU / Total DU according with condition | Condition: L2_REVIEW_END_TIME not empty, L2_FIRST_REVIEW_END_TIME not empty, L1_REVIEW_END_TIME not empty, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: L2_FIRST_REVIEW_END_TIME - L1_REVIEW_END_TIME <= 7days. Denominator: Total DU | 0.8 | -
4.2 | QCL1-QCL2 | QCL2 Reject Rate | Percentage of all L2 being rejected to the total number of QCL2 review tasks in the statistical period. | Count DUs of L2_REVIEW_END_TIME is not empty and QC STATUS is not empty and L2 not first time pass / Total DU according with condition | Condition: L2_REVIEW_END_TIME not empty, L2_FIRST_REVIEW_END_TIME not empty, STATUS not Closed, INSTALL_QC_FLAG = 'Required QCL1', Valid DU = 'Y'. Numerator: L2_REVIEW_END_TIME - L2_FIRST_REVIEW_END_TIME > 15seconds. Denominator: Total DU | 0.2 | -
5 | Valid DU | - | 1. Philippines: Valid DU = 'Y' QCL1 FLAG = 'Y' or Empty b. Non Valid DU ='N' i. QCL1 date > MOS actual end date (more than 5 days), eg: MOS-QC L1 duration > -5 (-6, -7, -8 onwards) ii. Globe Project , Task Flow name = "Tower Retro Activity' 2. Other Rep Office: Valid DU = 'Y' | - | - | - | -
6.1 | Exclude List | Exclude QC Singapore | 56A0D0B project: Data extraction logic: (Exclude) Inbound and outbound templates are filtered. The service type is QC-TE, QC-DC, and the status is Closed, Pass With Minor Issues, or Executing. 'To Be Reviewed','To Be Executed', 'Reviewing', 'Rejected' | - | - | - | -
6.2 | Exclude List | Exclude QC Philippines | Project 565446E', '56A0EAY: Data extraction logic: Filter the Site Verify template. The business type is'QC-TE' or'QC-DC'. The status is'Closed' or'Pass With Minor Issues', 'Executing','To Be Reviewed','To Be Executed', 'Reviewing', 'Rejected' | - | - | - | -
6.3 | Exclude List | Exclude QC Malaysia | Data extraction logic: Use the Acceptance template. The status is Closed, Pass With Minor Issues, Executing, To Be Reviewed, To Be Executed, Reviewing, or Rejected. | - | - | - | -
6.4 | Exclude List | Exclude QC Cambodia | Data extraction logic: Filter (Exclude) Dismantled, filter business types: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', status:'Closed','Pass With Minor Issues', 'Executing','To Be Reviewed','To Be Executed', 'Reviewing', 'Rejected' | - | - | - | -
6.5 | Exclude List | Exclude QC Myanmar | Data extraction logic: filter (Exclude) 8. Dismantle Materials Return, filter business type: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', status' Closed','Pass With Minor Issues', 'Executing','To Be Reviewed','To Be Executed', 'Reviewing', 'Rejected' | - | - | - | -
6.6 | Exclude List | Exclude QC Thailand | Data extraction logic: Filter by Installation-Completed, filter by business type: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', status: Closed,'Pass With Minor Issues', 'Executing','To Be Reviewed','To Be Executed', 'Reviewing', 'Rejected' | - | - | - | -
6.7 | Exclude List | Exclude QC Indonesia | Data extraction logic: Filter (Exclude) M-05a SV QC, M-08b Dismantle RAN, filter business types: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', status' Closed','Pass With Minor Issues', 'Executing','To Be Reviewed','To Be Executed', 'Reviewing', 'Rejected' | - | - | - | -
6.8 | Exclude List | Excluded Project | VIETNAM = ['Vietnam VNPT & MBF Account Dept'], SOUTH ASIA = ['56A0HWX', '56A04W0'] | - | - | - | -

## Chn
列 | 控制点 | 指标 | KPI定义 | KPI公式 | 规则 | 基线 | SLA
1 | MOS-QCL1 | MOS-QCL1周期 | 统计期内的DU范围从MOS到QC第一审核完成的平均周期。 | 平均值：总和（MOS-QCL1周期）/当月根据筛选条件的总MOS | 条件： MOS实际& QCL1日期不为空 MOS-QCL1周期>=0 计算： 平均值（MOS-QCL1时长） | QC - QC 14天 / PAT 21天 | -
1.1 | MOS-QCL1 | 一条流达成率 | MOS-QCL1在xx天内完成DU数/MOS在统计期内需完成QCL1的DU总数 | （QC L1审批完成时间- MOS实际结束时间）<=14天DU/当月MOS总数量 | 分子： MOS日期& QCL1日期不为空 MOS-QCL1持续时间>=-5 基线<= 14天（默认值） 分母： MOS总日期 | 80% | -
2 | MOS-安装 | MOS-安装周期 | 统计期内的DU范围从MOS到安装完成的平均周期。 | 平均值：总和（MOS-INSTALL周期）/当月根据条件的总MOS | 条件： MOS日期&安装日期不为空 MOS-INSTALL时长>=0 计算： 平均（MOS-INSTALL时长） | - | 7天
2.1 | MOS-安装 | 入场及时率 | 从MOS实际完成日期推后三天有打卡的DU数/MOS完工DU数 | 最早打卡日期- MOS实际结束日期<=3天/当月总MOS | 分子： MOS实际结束日期-打卡日期<=3天) 分母： MOS总日期 | 80% | 3天
2.2 | MOS-安装 | 作业连续性 | 队伍是否持续上站打卡直到QCL1完成 计算公式：同个队伍在MOS-QCL1内的打卡天数/MOS-QCL1总天数 | MOS-INSTALL / MOS-INSTALL周期之间的时钟天数 | 条件： MOS日期和安装日期不为空 分子： 之间的打卡记录(MOS-INSTALL) 分母： MOS-INSTALL时长+1 | 70% | -
2.3 | MOS-安装 | 二次派送率 | DN派送>=2的站点数/MOS完工的站点总数（不按DUID） 1.分子：取站点下所有DN，DN同天处理为一个DN，对DN数量大于等于2的站点计数。(对比3个月） 2.分母： 已经完成站点签的站点，去重，汇总 | 统计站点SITE_COUNT >=2 /站点ID总数 | 分子： 统计站点站点数量>=2 分母： 站点总ID | 15% | -
3 | 安装- QCL1 | 安装-QCL1周期 | 统计期内的DU范围从安装到QC第一审核完成的平均周期。 | 平均值：总和（安装-QCL1期间）/根据当月条件的总安装 | 条件： 安装实际结束- QCL1日期不为空 安装-QCL1周期>=0 计算： 平均（安装-QCL1持续时间） | QC - QC 7天 / PAT 14天 | -
3.1 | 安装- QCL1 | QC及时入场率 | 从安装实际完成后三天内执行QC任务（QC Save Start Time)/安装完工DU数 | QC保存开始日期-安装实际结束时间<=3天/总DU,qc_submit_flag='Y' | 条件: 保存_起始_日期不为空, 首次_提交_时间不为空, 安装_QC_标识 = '需要QCL1', 有效DU = 'Y'. 分子: 保存_起始时间 - 实际安装完成时间 <= 3天. 分母: 所有DU | 90% | -
3.2 | 安装- QCL1 | QC采集及时率 | 从QC任务开始（Save Start Time)至到QC任务第一次提交时间/提交QCL1任务总数 | 首次提交批准时间-保存BEGIN_DATE<=3天/具有QC_COLLE_MINS_DIFF的DU合计<=3天 | 条件: 保存_起始_日期不为空, 首次_提交_时间不为空, 安装_QC_标识 = '需要QCL1', 有效DU = 'Y'. 分子: 首次_提交_时间 - 保存_起始时间 <= 3天. 分母: 所有DU | 80% | -
3.3 | 安装- QCL1 | QCL1及时审批率 | （L1审批完成时间-QC上次提交时间）任务数/手工审批任务总数 | L1_审核_结束_时间 - L1_首次_提交_时间 <= 1 Days / 总DU数，筛选条件QC1_FLAG = Y | 条件： L1_评审_完成时间不为空，首次_提交_时间不为空，安装_QC_标识='所需QCL1'，有效DU='Y'。 分子：L1_评审_完成时间-保存_起始_日期<=3天。分母：DU合计 | 90% | -
3.4 | 安装- QCL1 | QCL1首次通过率(FTPR) | 首次通过QCL1审批的DU数量 | L1_审核_结束_时间-L1_首次_审核_结束_时间/具有QCL1的DU合计_标志=Y | 条件： L1_评审_完成时间不为空，L1_首次_评审完成_时间不为空，安装_QC_FLAG='所需QCL1'，有效DU='Y'。 分子：L1_评审完成_时间-L1_首次_评审完成_时间<= 15秒。 分母：DU合计 | 90% | -
4 | QCL1-QCL2 | QCL1-QCL2周期 | 统计期内从完成QCL1审批完成到QCL2审批完成平均时间。 | 平均值：总和（QCL1-QCL2期间）/本月根据条件的总QCL1 | 条件： QCL2日期和QCL1日期不为空 MOS-QCL1周期>=0 计算： 平均值（MOS-QCL1时长） | 14天 | -
4.1 | QCL1-QCL2 | QCL2及时评审率 | （L2首次评审完成日期-L1审批完成日期）任务数/L1审批的任务总数 | 计数（L2_第一次_审查_结束_时间-L1_审查_结束_时间）<=7天DU/QCL2的总DU_标志='Y' | 条件：L2_评审完成_时间不为空，L2_首次_评审完成_时间不为空，L1_评审完成_时间不为空，安装_QC_FLAG='所需QCL1'，有效DU='Y'。分子：L2_首次_评审完成_时间-L1_评审完成_时间<=7天。分母：DU合计 | 80% | -
4.2 | QCL1-QCL2 | QCL2拒绝率 | 统计周期内所有L2被拒绝的占QCL2评审任务总数的百分比。 | L2_RECREC_END_TIME不为空且QC STATUS不为空且L2非首次通过的DU数量/有条件的DU总数 | 条件：L2_评审完成_时间不为空，L2_首次_评审完成_时间不为空，状态不关闭，安装_QC_FLAG='所需QCL1'，有效DU='Y'。分子：L2_评审完成_时间-L2_首次_评审完成_时间>15秒。分母：DU合计 | 10% | -
5 | 有效DU | - | 1. 菲律宾: 有效DU = 'Y' QCL1 FLAG = 'Y' or 空 b. 无效 DU ='N' i. QCL1时间 > MOS 实际完成时间 (超过 5天), eg: MOS-QC L1周期 > -5 (-4, -3, -2 以上) ii. Globe项目 , Task Flow name = "Tower Retro Activity' 2. 其他代表处: 有效 DU = 'Y' |  |  | - | -
6.1 | 剔除清单 | 新加坡QC剔除 | 56A0D0B项目:取数逻辑: (剔除) Inbound and outbound 模板筛选. 业务类型 QC-TE, QC-DC, and the 状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.2 | 剔除清单 | 菲律宾QC剔除 | 项目'565446E', '56A0EAY: 取数逻辑: 剔除 Site Verify 模板。 业务类型 QC-TE, QC-DC, and the 状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.3 | 剔除清单 | 马来QC剔除 | 取数逻辑: 使用 Acceptance 模板。 业务类型 QC-TE, QC-DC, and the 状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.4 | 剔除清单 | 柬埔寨QC剔除 | 取数逻辑: 筛选 (剔除) Dismantled, 业务类型: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', 状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.5 | 剔除清单 | 缅甸QC剔除 | 取数逻辑: 筛选 (剔除) 8. Dismantle Materials Return, 业务类型: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS',状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.6 | 剔除清单 | 泰国QC剔除 | 取数逻辑: 筛选（剔除） by Installation-Completed, 业务类型: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', 状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.7 | 剔除清单 | 印尼QC剔除 | 取数逻辑: 筛选 (剔除) M-05a SV QC, M-08b Dismantle RAN, 业务类型: QC-TE', 'QC-DC', 'QC-CW', 'QC-ICS', 状态 为“关闭”, “Minor问题通过”， '待审批','待执行', '审批中', '被拒' |  |  | - | -
6.8 | 剔除清单 | 项目QC剔除 | VIETNAM = ['Vietnam VNPT & MBF Account Dept'], SOUTH ASIA = ['56A0HWX', '56A04W0'] |  |  | - | -